## Computation of Costs
PRELIMINARY COMPUTATION OF COST
In The Matter Of:
BEECHTREE DRAIN | [6 empty] | MDOT
OTTAWA COUNTY, MI | [6 empty] | Supplemental
1 | Cost Of Laying Out And Designating Drainage District (BOD Preparation) |  |  |  |  | 4000 |  | 4000 from SR/197
2 | Compensation Paid Board Of Determination |  |  |  |  | 1000 |  | ??
12.34%
3 | Contracts For Construction
|  |  | Fence/Sprinkler System Allowance | 4000
|  |  | Open Ditch Maintenance | 5000 |  |  | 4000 | McGilley's
|  |  | Emergency Pumping | 72900 |  |  |  | DeWind + Quantum Mob & Demob
|  |  | South Pump Installation | 40050 |  |  |  | Superior Golf Concepts & 3000 for Electrician
|  |  | Timber Dunes Storm Sewer | 159570.35 |  |  | 19690.9812 | Quantum
|  |  | Timber Dunes Open Ditch | 35228.57 |  |  | 4347.2055 | Randy Meyer
|  |  | Consumers Construction | 10000
|  |  | Pump Station Construction | 0
|  |  | Revised Gravity Drainage Solution | 128000
|  |  | Interconnecting Storage Basins | 145000 |  |  | 17893
|  |  | Future Maintenance and Pump Operation | 20000
619748.92
4 | Engineering, Design
|  |  | Study and Report/Boundary 197 |  |  | 4152.25
|  |  | Preliminary Design |  |  | 42100 | 5195.14
|  |  | Final Design |  |  | 73000 | 9008.2 | 102000
|  |  | Clubhouse Outlet |  |  | 32000 | 3948.8 | 42300
|  |  | Soil Borings |  |  | 10300
|  |  | Emergency Response Coordination |  |  | 9763
|  |  | Construction Documents, Bidding, and Day of Review |  |  | 19000
190315.25
5 | Easement Acquisition |  |  |  |  | 10000 |  | 10000 from FD
6 | Other Expenses
|  |  | Drain Office Adminstration & Legal | 17220.97 |  |  |  | 14791.15 | For FSBR | 2429.82 | For Drain Office Admin
|  |  | Postage, Day Of Review Notices | 400
|  |  | Bonding Legal | 10000
|  |  | Cost of Appeal | 10000
37620.97
7 | Cost Of Inspection, Construction Engineering & Material Testing
|  |  | Construction Administration |  |  | 30000 | 3702 | 15000 from Timber Dunes and 15000 Pump Station
|  |  | Construction Inspection - Timber Dunes |  |  | 47000 | 5799.8
|  |  | Construction Inspection - Clubhouse Outlet |  |  | 45500 | 5614.7 | PLF To talk to House
|  |  | Construction Staking |  |  | 7500 | 925.5 | 3000 from Timber Dunes and 4500 from Pump Station
|  |  | As-Built Drawings |  |  | 3000 | 370.2
|  |  | As-Built Survey |  |  | 2000 | 246.8 | 135000
325315.25
8 | Publishing Notices |  |  |  |  | 2000
|  |  | Gross Sum Of Expenses |  |  | 999685.14
|  |  | Contingent Expenses (Includes Bond Discount) |  | 10% | 99968.514
|  |  | Total Computed Cost Of Constructing Drain |  |  | 1099653.654 |  | 7.343%
[8 empty] | 4.53 | Make up.
|  | TOTAL TO BE ASSESSED ----------------------------------------------------------------------------------------------------------- |  |  |  | 1099653.654 |  | 168466.9398
Less Pre Paid Assessment--------------------------------------------------------------------------------------------------------
|  |  | American Dunes |  |  | 144198.33
|  |  | MDOT |  |  | 168520
|  |  | Others? |  |  | 0
| TOTAL AMOUNT TO BE BORROWED ----------------------------------------------------------------------------------------------------- |  |  |  |  | 786935.324 | 80742.3267 | 123234.0717
[6 empty] | MDOT Supplmental % | 10.26%
[6 empty] | MDOT 14A % | 7.66%
[6 empty] | MDOT Total Percent | 17.92%
[6 empty] | MDOT Estimated Total | 141021.5725

## Sheet1
Maint
Invoice No | Total
70165 | 1597.15
11673 | 963.04
12077 | 1421.75
422 | 1432.65
11508 | 1100
835 | 5400
10896 | 80
11085 | 175
890703 | 189.4
890703 | 60
70217 | 646.25
5559 | 185
11724 | 1316.6
12034 | 195
12133 | 310
15071.84